## Slide 1: Humanitarian Programme Cycle (HPC) FSL Cluster Timeline 2023
Timeline | 2024 HPC Process Description
8th September to 19th October | Finalizing Sectoral PiN / FSL Target / Unit Cost FSLC HRP Strategy (workshop report validation by SAG/CLAs), Cluster target and Costing (Unit Cost), IPC Analysis & Findings, Submission of FSL PiN, Severity, Target and Funding requirement, JIAF 2.0 workshop and Endorsement of PiN & Target.
9th October | Facilitate FSL Partners training on HPC module by OCHA Virtual orientation to NGO Partners on the online module of the Humanitarian Program Cycle
19th October | Cluster narrative submission to OCHA Submission of cluster narrative inputs for the planning document (combined HNO/HRP)
20th October | Cluster targets by indicators on RPM Cluster IMOs will finalize and upload FSL targets by indicators on Response Planning and Monitoring (RPM) Module
6th & 20th September 4th & 18th October | Ad-hoc FSLC Meeting on HRP 2024 (Note: 20th October – Opening of project module for project submission) Re-orientation on FSLC Strategy 2024-2026, Project Sheet Filling Criteria & step-by-step guidance, Guidance on Cross-cutting themes Re-organize the repository and upload the guidelines / standards (Ongoing, until 4th October and beyond)
3rd to 17th November | Vetting & Selection of 2024 HRP projects (Note: 20th November – Deadline for finalizing, submitting and approving projects) Project sheet download, Pre-screening, SRC formation and orientation, Grouping & assigning of projects to SRC teams, Review & Scoring Finalizing the partners selection and FSLC submit the final scorecard and the list of selected partners to OCHA

## Slide 2
Humanitarian Response Plan (HRP) – 2024
Project Sheet Filtering Criteria
Must be an operational partner in 2022 and 2023: currently there are 165 partners eligible
Partners (2022 and Jan – Sept. 2023) reporting by Cluster Objectives
5W reporting in 2023:
  CO1: Food Assistance: 71 partners (excludes WFP partners approx. 40)
  CO2: Crop-related livelihood kits: 114 partners (excludes FAO partners approx. 44)
  CO2: Livestock: 19 partners reporting (excludes FAO partners approx. 9)
  CO3: Training: 124 partners
  HRP 2022 and 2023 partners that have NOT reported on Financial Tracking Service (FTS) – please do it now!! Thank you for those HRP and Non – HRP partners who also reported FTS in 2023;
And of course, the quality of the project sheet proposal