## Slide 1
Rohingya and host communities response
Food Security Sector – Cox’s Bazar
Tuesday 23rd of January 2018, 10:00 – 11:00
Notes: v

## Slide 2: AGENDA
Introduction and welcome
General Food Distribution round 8 update
JRP Project template
Market price monitoring - new questionnaire (VAM)
PDM presentation by Save the children
Energy and Environment TWG update
AoB (4Ws, livelihoods WG,… )

## Slide 3: GFD Round 8 ongoing
Round 8: distribution started the 16th of January and will last until the 28th of January, WFP and 6 NGOs (2 NGOs complementary food assistance)
HHs reached as per 20th of January: 61,065
Refugees relocations support in coordination with UNHCR/IOM

## Slide 4: General Food Distribution Round 8 – ongoing distribution total household reached 61,065 by location
Chart: Total HH Reach as Of 20 January 2018 GFD Round 8
| Bagghona | Balukali 1 | Balukali 2 | Block D-5 | Burma Para | Chakmarkul | Hakimpara | Jadimura | Jamtoli | Lambasia | Leda | Mainnergona | Modhur chara (1) | Modhur chara (2) | Modhur chara (3) | Modhur chara (4) | Shamlapur | TV Tower
Total | 2028 | 4062 | 4351 | 4300 | 3974 | 990 | 3602 | 3094 | 4597 | 6324 | 2352 | 5124 | 3477 | 2839 | 3179 | 2313 | 1235 | 3224

## Slide 5: Summary of GFD Round 8 from 16th January to as of 20th January 2018 – with MT of food

## Slide 6: JRP proposals TEMPLATE
A.1 Project Template for Partners.xlsx

## Slide 7: JRP Timeline
Project portfolios To 21 February | 1 February – 9 February | 10 days | Partners | Partners draft projects and submit to Sector Coordinators by 9 February. | JRP and project templates and guidance shared with partners 1 February Partner projects due to Sector Coordinators 9 February
 | 10 February – 17 February | 1 week | ISCG / Sector Coordinators | Sector level peer review of projects with Sector Peer Review Teams. | Sectors to establish Peer Review Teams 1 February Final project portfolios due 18 February
 | 18 February – 24 February | 1 week | ISCG | ISCG review and consolidation. Consolidated draft due to sector coordinators and SEG by 24 February. | Consolidated draft: 24 February
 | 28 February | SEG REVIEW | SEG | SEG review with Sector presentations (format TBC) | 
 | 1 March |  |  | Rohingya Refugee Crisis Response Plan released. | 

## Slide 8: Market Monitoring - Revised
Food Security Sector CXB

## Slide 9: Review
12 + 2 key markets
Wholesalers / retailers / petty traders (3 per trader)
Every 2 weeks
Food / shelter / energy / hygiene / labor / transportation / others
Objectives:
  Price trend monitoring
  Input for market based interventions

## Slide 10: Questionnaire Market Monitoring draft final.docx

## Slide 11: Markets and partners
ACF
IFRC
Solidarites
DRC
Mutki
Handicap International
World Vision
Oxfam
Market | Partner | new
Ukhiya City | ACF | Mukti
Kutupalong | ACF | Oxfam
Balukhali | ACF | WVI/ACF
Teknaf | ACF | ACF
Thangkhali Bazar |  | WVI/Agrajattra
Court Bazar | IFRC | Mukti
Palongkhali Bazar | IFRC | Peniapil/Agrajattra
Leda Bazar | Solidarites | WVI
Shamlapur Bazar | Solidarites | 
Nhilla Bazar |  | 
Nayapara Bazar |  | Oxfam
Unchiprang Bazar | DRC | 
Chaktai market, Chittagong |  | 
Khanganj market, Chittagong |  | 

## Slide 12: Focal Points
Organization | Focal Points
ACF | Malek fsldrrpm-cox@bd.missions-acf.org, Mahadi fc-cox@bd.missions-acf.org, Md. Akbar Hossen akbarhossen2016@gmail.com, Md. Belal Uddin akon.belal.bm1989@gmail.com
IFRC | Ziaul Haque Himel ziaul.himel@ifrc.org
Solidarites | ATIK MAHMUD tek.meal.off1@solidarites-bangladesh.org, Manir MEAL ASSISTANT tek.meal.ast@solidarites-bangladesh.org, ‘Field Cordinator - Teknaf (SI)' tek.field.co@solidarites-bangladesh.org
DRC | Rachid Moujaes rachid.moujaes@drc.dk, Replacement to come (Contact TBC)
World Vision | Dongju dongju_kim@wvi.org
Handicap International | Amandine pmbasic@hibd.org
Mukti | Ashok Sarkar ashoksarkar59@gmail.com, Shntanu Sekhor shantanubd_roy@yahoo.com, Homayon Kabir homayonchy@gmail.com

## Slide 13: Timeframe
Every 2 weeks
Data collection start: 26th January
Next round: 15th February
Following round: End of February
Reminder sent to the focal points

## Slide 14
PDM presentation by Save the children

## Slide 15: ENERGY & ENVIRONMENT Technical Working Group

## Slide 16: COORDINATION STRUCTURE
ENERGY & ENVIRONMENT TECHNICAL WORKING GROUP
SHELTER/NFI SECTOR
SITE MANAGEMENT SECTOR
FOOD SECURITY SECTOR
CO-CHAIR
STAKEHOLDERS INVOLVED
IN ENERGY AND ENVIRONMENT
Partnership:
Government
GACC

## Slide 17: WORKING AXIS
Access to alternative cooking fuel and improved cook stoves (preferably through green and clean energy) is increased
The natural resource base is maintained and restored
Environmental impacts of the refugee crisis are reduced and ameliorated(DRR)
Sustainable and affordable energy technologies are promoted to roll out innovative, cost-effective, environment friendly and energy-efficient systems
TARGETS
REFUGEES
HOST COMMUNITIES

## Slide 18: AREA OF WORK
Action oriented group
Generation of innovative solution
Technical advice / knowledge management
Coordination with energy and environment stakeholders
Cross-cutting with relevant sectors (Wash-Protection …)
Close linkages withthe Livelihoods, DRR and Host Community TWG
Advocate for and guide resource mobilization through relevant mechanisms or calls for proposal from donors.
Connect with and support relevant government-led structures
Close linkages will be made with the Livelihoods, DRR and Host Community Technical Working Groups.

## Slide 19: NEXT ACTIONS
Identify energy and environment actors
Gather information on fuel and stoves deployed in CXB (survey)
Gather information about energies in general – electricity based
Technical support and monitoring of LPG project (FAO-IOM-UNHCR-WFP)
CONTACT
Benoît MAZY
01701 208946
benoit.mazy@wfp.org

## Slide 20: AoB
4Ws to report by Thursday 25th : include food assistance and livelihoods activities;
Livelihoods WG on Thursday 25th January at 9:30 WFP meeting room

## Slide 21
THANK YOU!